## Sheet1
Agile Project Plan
Project Name | Covid-19 Tracking App
Project Manager | Quang Tran
Project Deliverable | Release Plan (Sprint 5 Planning)
Scope Statement | This deliverable covers all the features to be completed by the end of Sprint 5 and includes the start and end dates, the responsible and the status for each covered feature.
Start Date | 2022-04-07
End Date | 2022-04-18
Overall Progress | 25%
Task Name | Responsible | Start | End | Days | Status
Sprint 5 | All team members | 2022-04-07 | 2022-04-18 | 11 | In progress
Issue-38 | Samantha G. and Steven M. | 2022-04-07 | 2022-04-12 | 5 | In progress
Issue-42 | Tushar R. and Laila A. | 2022-04-07 | 2022-04-12 | 5 | Not started
Issue-45 | Saleha T. and Hoda N. | 2022-04-07 | 2022-04-12 | 5 | Not started
Issue-41 | Samantha G. and Marwa K. | 2022-04-10 | 2022-04-16 | 6 | In progress
Issue-46 | Ali Z. and Hoda N. | 2022-04-11 | 2022-04-16 | 5 | Not started
Issue-44 | Ali Z. and Quang T. | 2022-04-14 | 2022-04-18 | 4 | Not started
Formulas:
Start = [Start, row below]