## Sheet1
Issue ID | Title | As | I want | so | Feature/Epic | Priority / Business Value | Story Point / Effort/ | Risk | MoSCow | Sprint | Given | When | Then
2 | Arrange Appointments | Doctor | I want to be able to arrange appointments with a COVID-19 patient | I can send notifications to the patient (email or SMS). |  | 1 | 13 | High | M-must | Sprint 3 | The user is logged in as a doctor | The user clicks on a patient to organize an appointment. | The user is shown the patient with a way to make an appointment and notify the patient.
3 | Prioritize Patient Updates (flag) | Doctor | to raise flags on certain COVID-19 patients | that their updates are prioritized over others. |  | 1 | 5 | Low | M-must | Sprint 2 | The user is logged in as a doctor, health official, or immigration officer and is on a patient profile | The user clicks on the "flag" | The application priorities the COVID-19 patient
3 | Prioritize Patient Updates (flag) | Health Official | to raise flags on certain COVID-19 patients | that their updates are prioritized over others. |  | 1 | 5 | Low | M-must | Sprint 2 | The user is logged in as a doctor, health official, or immigration officer and is on a patient profile | The user clicks on the "flag" | The application priorities the COVID-19 patient
3 | Prioritize Patient Updates (flag) | Immigration Officer | to raise flags on certain COVID-19 patients | that their updates are prioritized over others. |  | 1 | 5 | Low | M-must | Sprint 2 | The user is logged in as a doctor, health official, or immigration officer and is on a patient profile | The user clicks on the "flag" | The application priorities the COVID-19 patient
4 | Trace & notify COVID-19 patients | Health Official | to trace and notify the people with whom COVID-19 patients have been in contact, using their basic identification | that they can self-quarantine |  | 3 | 3 | Low | M-must | Sprint 2 | The user is logged in. | The user clicks the "notify all" button from the COVID-19 patient who has been in contact | The application sends a notification to all affected users.
5 | Dashboard view for doctors (patients' status, statistics, graph, etc) | Doctor | to have a dashboard view | that I can see an overview graph, my patients' status at a high level, and status updates |  | 1 | 8 | Medium | M-must | Sprint 1 | The doctor is logged in | The doctor clicks on the dashboard | The doctor is shown the dashboard with graphs and pertinent information
7 | LogIn / SignUp function (with user role system) | Patient | to have a login / signup system | users with different roles can log into their dashboard to view the appropriate contents. |  | 3 | 3 | Low | M-must | Sprint 1 | Patient is on the login page and inputs their password and email correctly | Patient clicks on the 'login' button | Patient will be redirected to the client dashboard
7 | LogIn / SignUp function (with user role system) | Admin | to have a login / signup system | users with different roles can log into their dashboard to view the appropriate contents. |  | 3 | 3 | Low | M-must | Sprint 1 | Admin is on the login page and inputs their password and email correctly | Admin clicks on the 'login' button | Admin will be redirected to the administration dashboard
9 | Patient Profile Details (for every patient) | Doctor | I want to see the list of details about a patient | that I can find out his/her status, temperature, weight, list of symptoms, etc. |  | 2 | 5 | Medium | M-must | Sprint 5 | The user is logged in as a doctor. | The user is on the Patients Page and clicks on the name of a patient | The application is redirected to the profile of that patient displaying a list of given details about the patient
10 | Notify doctor when status is re-updated on the same day | Patient | to notify the doctors when my status is re-updated on the same day | that they can have a look into my profile to see if I turned sick or recovered from Covid, or I simply made a mistake. |  | 3 | 3 | Low | M-must | Sprint 3 | The user is logged in as a patient. | The user modifies the previously completed status. | The application notifies the doctor(s) who are monitoring the patient about the change.
11 | Monitor status & symptoms of confirmed and unconfirmed patients | Doctor | monitor the status & symptoms of confirmed and unconfirmed patients | prescribe a suitable treatment for the patient. |  | 3 | 2 | Low | M-must | Sprint 3 | The user is logged in as a doctor or health official. | The user is on the Profile of the Patient page | The user can select confirmed from the dropdown.
11 | Monitor status & symptoms of confirmed and unconfirmed patients | Health Official | monitor the status & symptoms of confirmed and unconfirmed patients | prescribe a suitable treatment for the patient. |  | 3 | 2 | Low | M-must | Sprint 3 | The user is logged in as a doctor or health official. | The user is on the Profile of the Patient page | The user can select confirmed from the dropdown.
12 | Notify Covid-19 patients & self-quarantine individuals to update status daily | Doctor | notify those who are in self-quarantine or those who are confirmed with COVID-19 every day | that they can update their status through our platformthat they can update their status through our platform |  | 1 | 3 | Low | M-must | Sprint 4 | The user is logged in as a doctor or health official. | There are patients who have COVID-19 as a status (in self quarantine or confirmed). | The application sends them a daily notification to update their status.
12 | Notify Covid-19 patients & self-quarantine individuals to update status daily | Health Official | notify those who are in self-quarantine or those who are confirmed with COVID-19 every day | that they can update their status through our platformthat they can update their status through our platform |  | 1 | 3 | Low | M-must | Sprint 4 | The user is logged in as a doctor or health official. | There are patients who have COVID-19 as a status (in self quarantine or confirmed). | The application sends them a daily notification to update their status.
13 | Contact between patients & doctors | Doctor | contact my patients via email or chatbot within the application, and vice versa. | that they can receive immediate help |  | 3 | 8 | Medium | M-must | Sprint 2 | The user is logged in as a doctor or health official and is on the inbox page. | The user clicks on the "message" button for a specific patient. | The application opens a messenger window with the patient.
13 | Contact between patients & doctors | Health Official | contact my patients via email or chatbot within the application, and vice versa. | that they can receive immediate help |  | 3 | 8 | Medium | M-must | Sprint 2 | The user is logged in as a doctor or health official and is on the inbox page. | The user clicks on the "message" button for a specific patient. | The application opens a messenger window with the patient.
14 | Different visibility for different users | Doctor | see only the information that are relevant to me | that I am not overwhelmed by the unnecessary information OR having accessed on sensitive information about other users |  | 1 | 5 | Medium | M-must | Sprint 4 | The user is logged in. | The user is on the main page. | The web app only displays information that is relevant to the user that is logged in.
14 | Different visibility for different users | Health Official | see only the information that are relevant to me | that I am not overwhelmed by the unnecessary information OR having accessed on sensitive information about other users |  | 1 | 5 | Medium | M-must | Sprint 4 | The user is logged in. | The user is on the main page. | The web app only displays information that is relevant to the user that is logged in.
14 | Different visibility for different users | Immigration Officer | see only the information that are relevant to me | that I am not overwhelmed by the unnecessary information OR having accessed on sensitive information about other users |  | 1 | 5 | Medium | M-must | Sprint 4 | The user is logged in. | The user is on the main page. | The web app only displays information that is relevant to the user that is logged in.
14 | Different visibility for different users | Admin | see only the information that are relevant to me | that I am not overwhelmed by the unnecessary information OR having accessed on sensitive information about other users |  | 1 | 5 | Medium | M-must | Sprint 4 | The user is logged in. | The user is on the main page. | The web app only displays information that is relevant to the user that is logged in.
16 | Display / show that a patients' status updates have been reviewed | Doctor | to see which patient’s updates I have reviewed and which ones I have not reviewed yet | that I dont review over the same file again |  | 2 | 2 | Low | M-must | Sprint 3 | The user is logged in as a doctor and is on the patient page. | The user updates and reviews a a patient profile. | The application shows profiles that have not been reviewed yet.
17 | Identify how many patients are assigned to each doctor | Admin | to know how many patients are assigned to each doctor | that no doctor is overloaded while some others do not have as many patients |  | 1 | 2 | Low | M-must | Sprint 2 | The user is logged in as an administrator. | The user goes to the doctor and patients page. | The application displays all doctors and the number of patients they have been assigned.
18 | Assign doctors to patients | Admin | to assign doctors to incoming patients | the doctors are aware of which patients they are assigned |  | 1 | 5 | Medium | M-must | Sprint 2 | User sees patient without doctor assigned | User clicks on patient listed without doctor | User will be redirected to doctor assigning module
19 | Allow admin to manage client account (delete, re-assign role) | Admin | to manage client account | that I can perform actions such as delete account, or reassign role, etc. |  | 1 | 5 | Medium | M-must | Sprint 3 | The user is logged in an administrator. | The user is on a user account's page. | The application displays buttons ("Delete", "Reassign", "Modify") to modify the user account.
20 | [Additional] Re-assign a patient to another doctor | Admin | to re-assign a patient to another doctor when his/her doctor has an emergency to attend to | that the doctor focuses on the patient in the emergency |  | 5 | 5 | Medium | S-should | Sprint 2 | The user is logged in as an administrator and is on the patient list page. | The user clicks on the dropdown under "Assigned Doctor". | The application shows a list of doctors that are available.
21 | [Additional] Create API endpoints for our system | Admin | o have access on API endpoints of the application | that other applications (such as the one from the Government) can integrate with our platform, or vice versa. |  | 4 | 21 | High | C-could | Sprint 5 | The user is logged in as an administrator or a business user. | The user clicks on the "API" button. | The web application shows a contact form to fill out.
21 | [Additional] Create API endpoints for our system | Business User | o have access on API endpoints of the application | that other applications (such as the one from the Government) can integrate with our platform, or vice versa. |  | 4 | 21 | High | S-should | Sprint 5 | The user is logged in as an administrator or a business user. | The user clicks on the "API" button. | The web application shows a contact form to fill out.
22 | [Additional] Provide barcodes / QR codes or each record | Patient | to have a barcode / QR code for each individual record | that it can be shared / read by other media or other devices |  | 5 | 13 | High | S-should | Sprint 2 | The user is logged in | The user on on a patient profile | The application displays a QR code which houses the patient information
22 | [Additional] Provide barcodes / QR codes or each record | Admin | to have a barcode / QR code for each individual record | that it can be shared / read by other media or other devices |  | 5 | 13 | High | S-should | Sprint 2 | The user is logged in | The user on on a patient profile | The application displays a QR code which houses the patient information
22 | [Additional] Provide barcodes / QR codes or each record | Doctor | to have a barcode / QR code for each individual record | that it can be shared / read by other media or other devices |  | 5 | 13 | High | S-should | Sprint 2 | The user is logged in | The user on on a patient profile | The application displays a QR code which houses the patient information
22 | [Additional] Provide barcodes / QR codes or each record | Health Official | to have a barcode / QR code for each individual record | that it can be shared / read by other media or other devices |  | 5 | 13 | High | S-should | Sprint 2 | The user is logged in | The user on on a patient profile | The application displays a QR code which houses the patient information
22 | [Additional] Provide barcodes / QR codes or each record | Immigration Officer | to have a barcode / QR code for each individual record | that it can be shared / read by other media or other devices |  | 5 | 13 | High | S-should | Sprint 2 | The user is logged in | The user on on a patient profile | The application displays a QR code which houses the patient information
29 | Patient updates status everyday | Patient | to update my status everyday before a certain time | that it provides the doctor with details such as temperature, weight, list of symptoms, etc. |  | 1 | 8 | Medium | M-must | Sprint 3 | The user is logged in as a patient and is on their dashboard | The user clicks the "Add Status" button | The application opens a form with the details that need to be filled out
37 | Allow Patient to edit profile page | Patient | to be able to edit my profile | that doctor has all the up to date information |  | 2 | 8 | Low | M-must | Sprint 3 | Patient is logged in successfully | Patient clicks on profile page | the basic fields should be editable
38 | Patient dairy to update symptoms, locations | Patient | I would like to update my symptom + diary (building, the places have been using postcode, GPS ... diary is optional) daily | that doctors can view the patient's symptoms, and health officers can track patients' possible contact or self-quarantine. |  | 2 | 5 | Medium | M-must | Sprint 3 | The user is logged in as a patient. | The user clicks on edit diary. | The user is able to modify their symptoms + diary.
39 | Allow patient to view the basic info of the assigned doctor. | Patient | to view the basic info (e.g., name) of the assigned doctor. | that I know who is my assigned doctor and their information |  | 5 | 2 | Low | M-must | Sprint 3 | The user is logged in as a patient. | The user is on their profile page and clicks on the assigned doctor. | The basic information of the assigned doctor is displayed.
41 | Allow patients view the history of his/her updated symptoms + diary | Patient | to view the history of my updated symptom + diary | that I can see my health progress |  | 4 | 5 | Medium | M-must | Sprint 3 | The user is logged in as a patient. | The user clicks on their profile page. | The user's history of updated symptoms + diary is displayed
42 | (optional) Allow patient to view the message from the assigned doctor | Patient | to view the message from the assigned doctor (optional) | that I can communicate with the doctor |  | 5 | 3 | Low | C-could | Sprint 4 | The user is logged in as a patient. | The user clicks on the message notification. | The message is displayed.
43 | Allow doctor to view the history of symptoms for each patient. | Doctor | to view the history of symptoms for each patient | that I can give better medical advice |  | 4 | 2 | Low | M-must | Sprint 4 | The user is logged in as a doctor | The doctor clicks to view the profile of a specific user. | The history of symptoms is displayed for that specific user.
44 | (optional) Allow doctor to view the list of assigned patients & past assigned patients | Doctor | to view the list of assigned patients and past assigned patients (optional) | they know which patients to monitor |  | 5 | 2 | Low | C-could | Sprint 3 | The user is logged in as a doctor. | The doctor clicks on the list of assigned patient on their dashboard | The list of assigned patient is displayed.
45 | (optional) Allow doctor to change status of a patient to a non-patient | Doctor | to change the status of a patient to non-patient because he/she is cured (optional) | that I no longer monitor the patient |  | 5 | 3 | Low | C-could | Sprint 3 | The user is logged in as a doctor. | The patient has received the green light by a doctor | The status of the patient is changed to non-patient.
46 | (optional) Allow health officer to view statistics like the number of patients for each district daily | Health Official | to get some statistics like the number of patients for each district daily | that they know the overall trends and progress of the infection |  | 5 | 5 | Low | C-could | Sprint 3 | The user is logged in as a health officer. | The health officer clicks on their dashboard. | Specific statistics are displayed (e.g., number of patients for each district daily).
52 | Creating UI (code) for the client app | Patient | to have access to an app that helps me track covid-19 and communicate with health workers | that I can seek help and track my status |  | 3 | 21 | High | M-must | Sprint 2 | The user is a patient | The user signs up or signs into the client app. | The user is redirected to their personal client app dashboard.
66 | Filters for patient table | Doctor | I would like to filter my patient list | that I can better display my given patients. |  | 1 | 3 | Low | C-could | Sprint 5 | The user is logged in as a doctor. | The doctor clicks on top of patient table columns to filter the data. | Specific patients are listed based on the filter value.
80 | Create a similar "List of details" page for patients (on the patient app) | Patient | to see my list of details | that I can review my status, temperature, weight, list of symptoms, etc |  | 2 | 5 | Medium | M-must | Sprint 5 | The user is logged in as a patient. | The patient clicks on their profile | The application shows a list of given details about the patient.
89 | List of Patients with Details (Admin) | Admin | to see the list of patients with details (assigned doctor, upcoming appointment, etc) | that I can monitor each patient |  | 3 | 8 | Low | M-must | Sprint 5 | The user is logged in as an admin or doctor. | The patient clicks on patients | The application should be redirected to the Patients Page which shows a list of patients with details such as assigned doctors and more.
89 | List of Patients with Details (Admin) | Doctor | to see the list of patients with details (assigned doctor, upcoming appointment, etc) | that I can monitor each patient |  | 3 | 8 | Low | M-must | Sprint 5 | The user is logged in as an admin or doctor. | The patient clicks on patients | The application should be redirected to the Patients Page which shows a list of patients with details such as assigned doctors and more.
103 | Profile for patient | Patient | I want to see my profile with basic details such as my status, temperature, weight, address, etc | that I can know if the information is correct or needs modification. |  | 1 | 3 | Low | M-must | Sprint 2 | The user is logged in as a patient on client app. | The user clicks on profile button on bottom navbar. | The user is redirected to their profile displaying a list of given details about the patient.
182 | Appointments for client app | Patient | to be able to arrange appointments with my doctor | that I can receive notifications from them (email or SMS). |  | 1 | 8 | Medium | M-must | Sprint 5 | The user is logged in as a patient on client app. | The user clicks on appointment button on dashboard. | The user is shown the doctor with a way to make an appointment and notify the doctor.
238 | Admin List for superadmin to view/edit | Super Administrator | to manage admin app user accounts (all except Admins) | that I can authorize newly created accounts. |  | 1 | 5 | High | M-must | Sprint 4 | The user is logged in admin app as a super admin | The user clicks on the manage accounts sidebar button. | The application displays Newly Created Accounts List with relevant information.