## Sheet1
Agile Project Plan
Project Name | Covid-19 Tracking App
Project Manager | Quang Tran
Project Deliverable | Release Plan (Sprint 3 Planning)
Scope Statement | This deliverable covers all the features to be completed by the end of Sprint 3 and includes the start and end dates, the responsible and the status for each covered feature.
Start Date | 2022-02-24
End Date | 2022-03-16
Overall Progress | 20%
Task Name | Responsible | Start | End | Days | Status
Sprint 3 | All team members | 2022-02-24 | 2022-03-16 | 20 | In progress
Issue-4 | Tushar R. and Laila A. | 2022-02-24 | 2022-03-01 | 5 | Not started
Issue-39 | Hoda N. | 2022-02-24 | 2022-03-03 | 7 | Not started
Issue-37 | Saleha T. and Quang T. | 2022-02-24 | 2022-03-02 | 6 | In progress
Issue-29 | Samantha G. and Ali Z. | 2022-02-24 | 2022-03-05 | 9 | Not started
Issue-16 | Laila A. | 2022-03-01 | 2022-03-06 | 5 | In progress
Issue-10 | Saleha T. | 2022-03-01 | 2022-03-06 | 5 | Not started
Issue-38 | Quang T. and Steven M. | 2022-03-02 | 2022-03-09 | 7 | Not started
Issue-19 | Ali Z. and Marwa K. | 2022-03-02 | 2022-03-09 | 7 | Not started
Issue-2 | Quang T. and Samantha G. | 2022-03-02 | 2022-03-14 | 12 | Not started
Issue-41 | Quang T. | 2022-03-07 | 2022-03-15 | 8 | Not started
Issue-11 | Saleha T. and Samantha G. | 2022-03-09 | 2022-03-13 | 4 | In progress
Issue-46 | Ali Z. and Hoda N. | 2022-03-11 | 2022-03-16 | 5 | Not started
Issue-45 | Saleha T. | 2022-03-11 | 2022-03-16 | 5 | Not started
Issue-44 | Ali Z. | 2022-03-12 | 2022-03-16 | 4 | Not started
Formulas:
Start = [Start, row below]