## Sheet1
Agile Project Plan
Project Name | Covid-19 Tracking App
Project Manager | Quang Tran
Project Deliverable | Release Plan (Sprint 2 Planning)
Scope Statement | This deliverable covers all the features to be completed by the end of Sprint 2 and includes the start and end dates, the responsible and the status for each covered feature.
Start Date | 2022-02-03
End Date | 2022-02-23
Overall Progress | 30%
Task Name | Responsible | Start | End | Days | Status
Sprint 2 | All team members | 2022-02-03 | 2022-02-23 | 20 | In progress
Issue-3 | Saleha T. | 2022-02-03 | 2022-02-06 | 3 | In progress
Issue-17 | Marwa K. | 2022-02-03 | 2022-02-06 | 3 | In progress
Issue-16 | Laila A. | 2022-02-03 | 2022-02-07 | 4 | In progress
Issue-4 | Tushar R. | 2022-02-03 | 2022-02-07 | 4 | Not started
Issue-37 | Saleha T., Samantha G. and Hoda N. | 2022-02-03 | 2022-02-10 | 7 | Not started
Issue-80 | Ali Z. and Marwa K. | 2022-02-06 | 2022-02-11 | 5 | Not started
Issue-13 | Laila A., Quang T. and Tushar R. | 2022-02-06 | 2022-02-16 | 10 | In progress
Issue-22 | Laila A. and Saleha T. | 2022-02-07 | 2022-02-21 | 14 | In progress
Issue-18 | Marwa K. and Samantha G. | 2022-02-11 | 2022-02-18 | 7 | Not started
Issue-14 | Laila A. | 2022-02-11 | 2022-02-20 | 9 | Not started
Issue-20 | Marwa K. and Samantha G. | 2022-02-17 | 2022-02-23 | 6 | Not started
Formulas:
Start = [Start, row below]