## Sheet1
Agile Project Plan
Project Name | Covid-19 Tracking App
Project Manager | Quang Tran
Project Deliverable | Release Plan (Sprint 4 Planning)
Scope Statement | This deliverable covers all the features to be completed by the end of Sprint 4 and includes the start and end dates, the responsible and the status for each covered feature.
Start Date | 2022-03-17
End Date | 2022-04-06
Overall Progress | 35%
Task Name | Responsible | Start | End | Days | Status
Sprint 3 | All team members | 2022-03-17 | 2022-04-06 | 20 | In progress
Issue-4 | Tushar R. and Laila A. | 2022-03-17 | 2022-03-22 | 5 | In progress
Issue-39 | Hoda N. and Steven M. | 2022-03-17 | 2022-03-23 | 6 | In progress
Issue-29 | Saleha T., Samantha G. and Ali Z. | 2022-03-17 | 2022-03-23 | 6 | In progress
Issue-38 | Samantha G. and Steven M. | 2022-03-21 | 2022-03-28 | 7 | In progress
Issue-19 | Ali Z., Marwa K. and Steven M. | 2022-03-21 | 2022-03-28 | 7 | Not started
Issue-10 | Saleha T. | 2022-03-21 | 2022-03-26 | 5 | Not started
Issue-2 | Quang T. and Samantha G. | 2022-03-21 | 2022-03-31 | 10 | In progress
Issue-12 | Laila A. | 2022-03-22 | 2022-03-28 | 6 | Not started
Issue-140 | Steven M. | 2022-03-23 | 2022-03-28 | 5 | Not started
Issue-41 | Quang T. and Samantha G. | 2022-03-25 | 2022-04-02 | 8 | In progress
Issue-14 | Quang T. and Laila A. | 2022-03-26 | 2022-04-01 | 6 | Not started
Issue-43 | Tushar R. and Steven M. | 2022-03-26 | 2022-03-31 | 5 | Not started
Issue-238 | Samantha G. | 2022-03-27 | 2022-04-03 | 7 | Not started
Issue-80 | Ali Z., Marwa K and Samantha G. | 2022-03-28 | 2022-04-02 | 5 | In progress
Issue-42 | Tushar R. and Laila A. | 2022-04-01 | 2022-04-05 | 4 | Not started
Issue-46 | Ali Z. and Hoda N. | 2022-04-01 | 2022-04-05 | 4 | Not started
Issue-45 | Saleha T. and Hoda N. | 2022-04-01 | 2022-04-05 | 4 | Not started
Issue-44 | Ali Z. | 2022-04-01 | 2022-04-06 | 5 | Not started
Formulas:
Start = [Start, row below]